## Sheet1
Week # | To Do | Owned by | Deadline | Status | Comments
Week 8 - A Skeleton and a Plan | Discussion of Plan | Brian | 2019-08-10
Notes: coming up with a plan for the | Creation of Development Plan | Aaron | 2019-08-17
whole final term
Week 9 - Creation of prototypes | Development of prototype | Aaron | 2019-09-07
Notes: Basic functionality and flow working | Planning of User Testing | Brian | 2019-09-07
Week 10 - User Testing | User testing of the prototypes | Aaron | 2019-09-11
Notes: List will be basic; good enough for user testing and demo-ing | Documentation of the user testing | Brian | 2019-09-11
| Documentation of comments and feebacks | Brian | 2019-09-11
| Creation of new paper prototypes | Aaron | 2019-09-11
Week 11 - Final User Testing | User testing of the prototypes | Aaron | 2019-09-13
| Documentation of the user testing | Brian | 2019-09-13
| Documentation of comments and feebacks | Brian | 2019-09-13
Week 11 - Final User Testing
Week 12 - Creation of Digital Mockups | Create digital mockup using PowerPoint | Aaron | 2019-09-14
| Link digital mockup screens | Aaron | 2019-09-14
| Testing of Digital Mockup | Brian | 2019-09-14
Week 13 - Creation of Presentation | Create Powerpoint presentation | Brian | 2019-09-14
| Finalize Powerpoint content | Brian | 2019-09-19
| Development of Ionic application | Brian | 2019-09-19
| Update Github repository | Brian | 2019-09-19
Week 14 - Final Presentation | Revised Needfinding | Brian | 2019-09-20
| Revised Paper Prototype | Aaron | 2019-09-20
| Digital Mock-up of your paper prototype | Aaron | 2019-09-20
| Demo of hosted and liked digital mockup screens | Brian | 2019-09-20